## User Stories
Story ID | User Story | Business Requirement | Tasks | Sprint
SID-01 | As a seller, I want to list and sell my products in a single platform, so that I can reach a larger audience and manage my sales from one app. | Detailed analysis of business needs, user personas, and competitor research | 1. Requirement Gathering and Documentation | Sprint 1
SID-02 | As a user, I want to access the platform easily. | The platform needs to be user-friendly and responsive across devices. | 1. Set up project repositories and environment
2. Finalize project requirements.
SID-03 | As a user, I want a smooth and attractive shopping experience. | The UI should be intuitive, easy to navigate, and visually appealing. | 1. Create wireframes and prototyping for key pages. | Sprint 2
3. Design mobile-responsive version.
4. Finalize UI designs after feedback.
SID-04 | As a user, I want a User Friendly Experience in all devices | Creating responsive layout, navigations using appropriate frontend technologies | 1. Developing Frontend/ web pages | Sprint 3
SID-05 | As a user, I want to securely log in to the platform. | User login and account creation need to be secure and intuitive. | 1. Design user login flow.
2. Implement registration and login features.
3. Implement forgot password and security features.
4. Implement role-based access.
SID-06 | As an admin, I want to manage products effectively and track orders. | Admin should be able to view, add, edit, and delete products and track order status | 1. Develop product CRUD functionality. | Sprint 4
2. Add product categories and order tracking features
3. Implement product filtering options.
4. Test product and order management features.
SID-07 | As a customer, I want to purchase items easily and securely. | Cart should be easy to add/remove items and checkout should be secure. | 1. Build shopping cart functionality.
2. Implement checkout flow (address, payment methods).
SID-08 | As a customer, I need Payment gateway to pay for good or service | User should Securly pay for good and services | Integrate payment gateways like Paypal, RazorPay | Sprint 5
Testing payment gateway
SID-09 | As a customer, I want to leave feedback on products. | The platform should allow product reviews and ratings. | 1. Implement review and rating system.
2. Moderate reviews.
3. Test review system with different user profiles.
SID-10 | As an admin, I want to view platform performance metrics. | Admin needs to access real-time data and reports on platform performance. | 1. Design admin dashboard UI. | Sprint 6
2. Develop reports for sales, orders, and users.
3. Test dashboard functionality.
SID-11 | As a user, I want a flawless user experience. | Ensure all features work seamlessly across platforms. | 1. Perform final round of testing. | Sprint 7
2. Refine UI/UX based on feedback.
3. Ensure accessibility standards.
SID-12 | As a user, I want to access the final, fully functional platform. | The platform must be deployed to production without errors. | 1. Deploy the platform to the production environment. | Sprint 8
2. Perform final checks.
3. Launch platform publicly.

## Product Backlogs
E-Commerce Project
8 Months Development Timeline
User Story | Business Requirement | Tasks | Priority | Planned Hours | Used Hours | Status | Story point (Scale 1 to 8)
Month 1 & 2: Platform Setup, Initial Development, UI/UX Design
Focus on platform setup, UI/UX design, ensuring the foundation of the project is solid.
As a seller, I want to list and sell my products in a single platform, so that I can reach a larger audience and manage my sales from one app. | Detailed analysis of business needs, user personas, and competitor research | 1. Requirement Gathering and Documentation | High | 30 | 25 | Completed | 8
As a user, I want to access the platform easily. | The platform needs to be user-friendly and responsive across devices. | 1. Set up project repositories and environment | High | 18 | 12 | Complete | 5
2. Finalize project requirements.
As a user, I want a smooth and attractive shopping experience. | The UI should be intuitive, easy to navigate, and visually appealing. | 1. Create wireframes and prototyping for key pages. | Medium | 57 | 50 | Complete | 5
3. Design mobile-responsive version.
4. Finalize UI designs after feedback.
Month 3 & 4: Frontend Development, Product Management, Shopping Cart, Order Management
Development of Frontend Design, Authentication, product management, shopping cart, which are core features of the platform.
As a user, I want a User Friendly Experience in all devices | Creating responsive layout, navigations using appropriate frontend technologies | 1. Developing Frontend/ web pages | High | 30 | 29 | Completed | 8
As a user, I want to securely log in to the platform. | User login and account creation need to be secure and intuitive. | 1. Design user login flow. | Medium | 34 | 32 | Complete | 5
2. Implement registration and login features.
3. Implement forgot password and security features.
4. Implement role-based access.
As an admin, I want to manage products effectively and track orders. | Admin should be able to view, add, edit, and delete products and track order status | 1. Develop product CRUD functionality. | High | 36 | 36 | Complete | 8
2. Add product categories and order tracking features
4. Test product and order management features.
As a customer, I want to purchase items easily and securely. | Cart should be easy to add/remove items and checkout should be secure. | 1. Build shopping cart functionality. | Low | 10 | 9 | Complete | 4
2. Implement checkout flow (address, payment methods).
Month 5 & 6: Payment Gateway and Admin Dashboard
Focus on advanced features such as Payment Gateway, admin dashboards
As a customer, I need Payment gateway to pay for good or service | User should Securly pay for good and services | 1. Integrate payment gateways like Paypal, RazorPay | High | 20 | 18 | Complete | 8
2. Testing payment gateway
As a customer, I want to leave feedback on products. | The platform should allow product reviews and ratings. | 1. Implement review and rating system. | Medium | 14 | 10 | Complete | 5
2. Moderate reviews.
3. Test review system with different user profiles.
As an admin, I want to view platform performance metrics. | Admin needs to access real-time data and reports on platform performance. | 1. Design admin dashboard UI. | Medium | 33 | 32 | Complete | 5
2. Develop reports for sales, orders, and users.
3. Test dashboard functionality.
Month 7 & 8: User Analytics Integration, Final Testing, Deployment
Performance optimization, mobile optimization, and final deployment to production.
As a user, I want a flawless user experience. | Ensure all features work seamlessly across platforms. | 1. Perform final round of testing. | High | 51 | 48 | Complete | 8
2. Refine UI/UX based on feedback.
3. Ensure accessibility standards.
As a user, I want to access the final, fully functional platform. | The platform must be deployed to production without errors. | 1. Deploy the platform to the production environment. | High | 52 | 45 | Complete | 7
2. Perform final checks.
3. Launch platform publicly.

## Sprint Management
Sprint Management
Month | Sprint | Sprint Duration | Sprint Desc | Team Included | Sprint Wise Budget
Month 1 | Sprint 1 | 2 Weeks | Foundation, Requirement Gathering and Documentation | Business Analyst, Project Manager | 185000
| Sprint 2 | 2 Weeks | Platform Environment Setup, UI Designing | UIUX Designer, Full Stack developer, Frontend Dev, Backend Dev | 133125
Month 2 | Sprint 3 | 2 Weeks | Developing Frontend, Authentication system, Product management | Backend Dev, Full Stack Dev | 184523
| Sprint 4 | 2 Weeks | Order Management, Spopping cart, QA Testing | QA Tester, Fullstack Dev | 209000
Month 3 | Sprint 5 | 2 Weeks | Integrating Payment Gateway, tesing Secure Payment Methods, Implement review system | Backend Dev, Fontend Dev | 236856
| Sprint 6 | 2 Weeks | Designing admin dashboard, realtime reporting for sales, order, test dashboard | QA Tester, Fullstack Dev | 161460
Month 4 | Sprint 7 | 2 Weeks | Final testing and If product meet clients requirement and check SRS documentation | Project Manager, QA tester, Fullstack Dev, Backend Dev | 130750
| Sprint 8 | 2 Weeks | Deploy Product at Client’s environment | DevOps, Project Manager, Bussiness Analyst | 169286

## Sprint 1
Sprint No. | Start Date | End Date | Days | Sprint Goal | Tasks | Assigned To | Status | Comment | Planned hours | Story Point (Scale point 1 to 8) | Priority
1 | 2025-01-01 | 2025-01-15 | 11 | Focus on Requirement Gathering, platform setup, ensuring the foundation of the project is solid. | 1. Requirement Gathering | Business Analyst | Complete |  | 20 | 8 | High
[5 empty] | 2. Finalize project requirement | Business Analyst and Project Manager | Complete |  | 10 | 8 | High
[5 empty] | 3. Documentation | Project Manager | Complete |  | 10 | 8 | High
[5 empty] | 4. Set up project repositories and environment | Frontend, Backend, Fullstack Developer | Complete |  | 8 | 5 | Medium
Total Budget | Misc. Expense | Devloper Expense | Hardware/softwar/cloud/tools Expense |  | Toal Expense
45 Lakhs | 10000 | 145000 | 30000 |  | 185000
[8 empty] | Priority | Status
[8 empty] | High | Complete
[8 empty] | Medium | In Progress
[8 empty] | Low | Not Started
OverDue
Need Review
Approved
On Hold

## Sprint 2
Sprint No. | Start Date | End Date | Days | Sprint Goal | Tasks | Assigned To | Status | Comment | Planned Hours | Story Point (Scale point 1 to 8) | Priority
2 | 2025-01-16 | 2025-01-30 | 12 | Focus on creating UI/UX design, Wireframing, Prototyping and Mockups | 1. UI Designing | UI/UX Designer | Complete |  | 20 |  | High
[5 empty] | 1. UI/UX Design Finalization | UI/UX Designer | Complete |  | 12 |  | High
[5 empty] | 3. Creating responsive design for mobile devices | UI/UX Designer | Complete |  | 15 |  | Low
[5 empty] | 4. Feedback and Reviewing | UI/UX Designer, Project Manager | Complete |  | 10 |  | Medium
[12 empty] | Priority | Status
Total Budget | Misc. Expense | Devloper Expense | Hardware/softwar/cloud/tools Expense |  | Toal Expense | [6 empty] | High | Complete
45 Lakhs | 9375 | 80000 | 43750 |  | 133125 | [6 empty] | Medium | In Progress
[12 empty] | Low | Not Started
OverDue
Need Review
Approved
On Hold

## Sprint 3
Sprint No. | Start Date | End Date | Days | Sprint Goal | Tasks | Assigned To | Status | Comment | Planned Hours | Story Point (Scale point 1 to 8) | Priority
3 | 2025-02-01 | 2025-02-14 | 12 | Focus on Frontend Development, Creating Responsive Layout, Implementation of Auth System | 1. Frontend Development | Frontend Developer | Complete |  | 26 | 8 | High
[5 empty] | 2. Creating Responsive Layouts | Frontend Developer | Complete |  | 12 | 5 | Medium
[5 empty] | 3. Implementation of Auth System | Backend Developer, Fullstack Developer | Complete |  | 10 | 8 | High
[5 empty] | 4. Implementation role-based access | Backend Developer, Fullstack Developer | Complete |  | 8 | 5 | Medium
[5 empty] | 5. Adding Forget Password and Security Features | Fullstack Developer | Complete |  | 8 | 8 | High
[12 empty] | Priority | Status
[12 empty] | High | Complete
[12 empty] | Medium | In Progress
Total Budget | Misc. Expense | Devloper Expense | Hardware/softwar/cloud/tools Expense |  | Toal Expense | [6 empty] | Low | Not Started
45 Lakhs | 14523 | 140000 | 30000 |  | 184523 | [7 empty] | OverDue
Need Review
Approved
On Hold

## Sprint 4
Sprint No. | Start Date | End Date | Days | Sprint Goal | Tasks | Assigned To | Status | Comment | Planned Hours | Story Point (Scale point 1 to 8) | Priority
4 | 2025-02-17 | 2025-02-28 | 11 | Focus on Product Management, Order Tracking, Shopping Cart | 1. Develop CRUD Functionality for order and product management | Fullstack Developer, Backend Developer | Complete |  | 18 | 8 | High
[5 empty] | 2. Adding Product Category, Order Tracking | Frontend Developer, Backend Developer | Not Started | Implementation of add to cart, cart management and order tracking is incomplete (It will continue in sprint 5) | 10 | 5 | Medium
[5 empty] | 3. Build Shopping Cart and Check-out Navigations | Frontend Developer, Fullstack Developer | Not Started |  | 10 | 5 | Medium
[5 empty] | 4. Testing Features | QA Tester | On Hold |  | 8 | 4 | Medium
[12 empty] | Priority | Status
Total Budget | Misc. Expense | Devloper Expense | Hardware/softwar/cloud/tools Expense |  | Toal Expense | [6 empty] | High | Complete
45 Lakhs | 7000 | 177000 | 25000 |  | 209000 | [6 empty] | Medium | In Progress
[12 empty] | Low | Not Started
OverDue
Need Review
Approved
On Hold

## Sprint 5
Sprint No. | Start Date | End Date | Days | Sprint Goal | Tasks | Assigned To | Status | Comment | Planned Hours | Story Point (Scale point 1 to 8) | Priority
5 | 2025-03-01 | 2025-03-14 | 12 | Integration of Payment Gateway and Product Feedback | 1. Integrating Payment Gateway for transaction | Fullstack developer, Backend Developer | Complete |  | 12 | 5 | Medium
[5 empty] | 2. Testing Payment Gateway and improve security | Fullstack developer, Backend Developer | Complete |  | 8 | 5 | Medium
[5 empty] | 3. Implement feedback or rating stsyem | Frontend developer and backend developer | Complete |  | 8 | 4 | Medium
[5 empty] | 4. Testing Feedback system | QA Tester | Complete |  | 6 | 5 | Medium
4 |  |  |  | Focus on Product Management, Order Tracking, Shopping Cart | 2. Adding Product Category, Order Tracking | Fullstack developer, Frontend Developer | Complete |  | 10 | 8 | High
[5 empty] | 3. Build Shopping Cart and Check-out Navigations | Fullstack developer, Frontend Developer | Complete |  | 10 | 8 | High
[12 empty] | Priority | Status
[12 empty] | High | Complete
[12 empty] | Medium | In Progress
[12 empty] | Low | Not Started
|  | Total Budget | Misc. Expense | Devloper Expense | Hardware/softwar/cloud/tools Expense |  | Toal Expense | [5 empty] | OverDue
|  | 45 Lakhs | 9856 | 177000 | 50000 |  | 236856 | [5 empty] | Need Review
Approved
On Hold

## Sprint 6
Sprint No. | Start Date | End Date | Days | Sprint Goal | Tasks | Assigned To | Status | Comment | Planned Hours | Story Point (Scale point 1 to 8) | Priority
6 | 2025-03-15 | 2025-03-29 | 13 | Develop reporting for sales, order and improving Admin Dashboard | 1. Findout Key Metrics and develop report for sales and order | Data Analyst | Complete |  | 15 | 8 | High
[5 empty] | 2. Creating Visualization for reports | Data Analyst, Full Stack Developer | Complete |  | 10 | 5 | Medium
[5 empty] | 3. Testing dashboard funcationality | QA Tester | Need Review |  | 8 | 5 | Medium
Total Budget | Misc. Expense | Devloper Expense | Hardware/softwar/cloud/tools Expense |  | Toal Expense
45 Lakhs | 9460 | 127000 | 25000 |  | 161460
[12 empty] | Priority | Status
[12 empty] | High | Complete
[12 empty] | Medium | In Progress
[12 empty] | Low | Not Started
OverDue
Need Review
Approved
On Hold

## Sprint 7
Sprint No. | Start Date | End Date | Days | Sprint Goal | Tasks | Assigned To | Status | Comment | Planned Hours | Story Point (Scale point 1 to 8) | Priority
7 | 2025-04-01 | 2025-04-15 | 13 | Ensure all features work seamlessly across platform | 1. Perform Final Testing | QA Tester | Complete |  | 24 | 8 | High
[5 empty] | 2. Refine UI/UX based on feedback | UIUX Designer, Frontend Developer | Complete |  | 12 | 7 | High
[5 empty] | 3. Ensure accessibility standards for Diabled Persons | UIUX Designer, Frontend Developer | Complete |  | 15 | 5 | Medium
[12 empty] | Priority | Status
[12 empty] | High | Complete
[12 empty] | Medium | In Progress
| Total Budget | Misc. Expense | Devloper Expense | Hardware/softwar/cloud/tools Expense |  | Toal Expense | [5 empty] | Low | Not Started
| 45 Lakhs | 7500 | 107000 | 16250 |  | 130750 | [6 empty] | OverDue
Need Review
Approved
On Hold

## Sprint 8
Sprint No. | Start Date | End Date | Days | Sprint Goal | Tasks | Assigned To | Status | Comment | Planned Hours | Story Point (Scale point 1 to 8) | Priority
8 | 2025-04-16 | 2025-04-30 | 13 | Deploying Platform without error | 1. Deploy the platform to the production environment. | Developers | Complete |  | 20 | 8 | High
[5 empty] | 2. Perform final checks. | QA Tester | Complete |  | 12 | 8 | High
[5 empty] | 3. Launch platform publicly. | Developers | Complete |  | 20 | 5 | Medium
[12 empty] | Priority | Status
[12 empty] | High | Complete
[12 empty] | Medium | In Progress
Total Budget | Misc. Expense | Devloper Expense | Hardware/softwar/cloud/tools Expense |  | Toal Expense | [6 empty] | Low | Not Started
45 Lakhs | 7286 | 142000 | 20000 |  | 169286 | [7 empty] | OverDue
Need Review
Approved
On Hold

## Budget
Deveopers Salary Budget
Role | Monthly Salary | 4 Months | 8 Months | 1 Year
Project Manager | 50000 | 200000 | 400000 | 600000
Business Analyst | 40000 | 160000 | 320000 | 480000
UI/UX Designer | 30000 | 120000 | 240000 | 360000
Frontend Developer | 40000 | 160000 | 320000 | 480000
Backend Developer | 50000 | 200000 | 400000 | 600000
Full Stack Developer | 60000 | 240000 | 480000 | 720000
QA Tester | 37000 | 148000 | 296000 | 444000
Data Analyst | 40000 | 160000 | 320000 | 480000
Total Salary |  | 1388000 | 2776000 | 4164000
Tools, Licenses, and Miscellaneous Costs
Category | 1 Year
Tools & Licenses | 110000
Cloud Hosting & Infrastructure | 130000
Miscellaneous Expenses | 75000
Total Additional Costs | 315000
Total Project Budget
Duration | Salary Costs | Additional Costs | Total Budget
4 Months | 1388000 | 315000 | 1703000
8 Months | 2776000 | 315000 | 3091000
1 Year | 4164000 | 315000 | 4479000
Sprint Name | Budget | Month
Sprint 1 | 185000 | 1
Sprint 2 | 133125 | 1
Sprint 3 | 184523 | 2
Sprint 4 | 209000 | 2
Sprint 5 | 236856 | 3
Sprint 6 | 161460 | 3
Sprint 7 | 130750 | 4
Sprint 8 | 169286 | 4
TOTAL | 1410000